| Overview |  |  |
| --- | --- | --- |
| Introduction | Development of theme and proposed activities for 2018 Chemists Celebrate Earth Week. |  |
| Theme Team | Theme Team leaders: Michael B. McGinnis (CCA), Richard Rogers (PDP) Theme Team members: Alex Madonik (Chair), Rick Rogers (PDP Co-Chair), Jackie Erikson, George Fisher, Al Hazari, Sheila Kanodia, George Ruger, Sanda Sun, Cary Supalo |  |
| Timeline |  |  |
| Time Frame/ Deadlines | Role(s) Responsible | Tasks |
| Spring 2016 ACS Meeting | PDP | Name theme team chair, suggest sources for theme team members outside of CCA, requests volunteers from CCA |
| Summer 2016 | PDP | PDP Co-Chair recruits theme team members from outside PDP |
| Fall 2016 ACS Meeting | Theme Team, PDP | Report on final makeup of theme team including members from outside CCA |
| November 2016 | Theme Team, PDP, Staff | Conference call with Theme Team to generate first draft of theme document |
| January 2016 | Theme Team, Staff | Complete draft of document and share with PDP subcommittee. Get suggestions on additional themes, partners, activities, resources. |
| 2-3 weeks before Spring 2017 ACS Meeting | Theme Team, PDP, Staff | Work with ACS staff to get supplies for voting on title. |
| Spring 2017 ACS Meeting | Theme Team, Staff | Finalize top suggested activities and any holes/need for additional activities; select members to work on contest guidelines. All the decisions related to the theme are final by the Fall 2017 meeting. |
| Fall 2017 ACS Meeting | Everyone | Review materials selected for development in the publication. Finalize proposed partners list. Approve contest guidelines. |
| Winter 2017 – 2018 | Everyone | Assist ACS staff generating Celebrating Chemistry CCEW edition; review documents, activities, web links and interactive resources when requested. |
| Spring 2018 ACS Meeting | Everyone | Theme is launched – ACS publicizes theme. |
| Resources |  |  |
| Concept | Atmosphere, Soil/Plants, Recycling, or Water - Water – Chemistry of the Oceans |  |
| Theme Name | Dive Into Marine Chemistry |  |
| Theme Areas of Emphasis | These were carefully selected taking the National Science Education Standards into account. The areas relate to what upper elementary (4-6 grade) students are learning. - Solutions – salt in water - Density - salt concentration in water - Ecosystems – the ocean – fish, seaweed, diatoms, crustaceans - Environment – carbon dioxide changes ocean temperature and acidity - Food and other products from the ocean |  |
| Theme Rationale | Oceans make up over 70% of the Earth’s surface, and have not been the focus of an ACS Earth Day theme. They are of universal interest for this tenth anniversary celebration and the rebranding of Chemists Celebrate Earth Week. |  |
| Proposed Partners | Consider organizations whose mission and goals might match up with our own motivations for this program. Partnerships are most constructive when they are mutually beneficial. |  |
| Celebrating Chemistry Publication | The goal of the publication is to provide an entertaining, educational and engaging ‘leave behind’ tool for members out in their communities. Generally there is one introductory article and at least one other article that relates to the chemistry behind one of the two or three activities. Suggested Source: The Best of WonderScience Volume 1 Suggested Source: The Best of WonderScience Volume 2 Articles - Dive Into Marine Chemistry – Alex Madonik - Seaweed: The Marine Chemists – Sheila Kanodia - Fish is Brain Food! – George Fisher and George Ruger - Seaweed Thickeners in toothpaste and ice cream – Cary Supalo - Bioluminescence and deep sea creatures – Rick Rogers Activities - Oil Spill! – Alex Madonik - Salt Water Rainbows – Sanda Sun - Sea shells and calcium carbonate – Jackie Erickson - Brine Shrimp – Rick Rogers Meg A. Mole Interview Candidates - Frank Millero – George Fisher Games - Hidden Objects - Maze - Word Find - Web-Based Interactive Game Artwork - Cover - Diving mole (maybe Meg or Milli) in scuba gear diving by seaweed and fish Artwork - Centerspread - Mole floating on the Great Salt Lake, one surfing the ocean |  |
| Outreach Friendly Activities | Please give at least three activities that are appropriate for an outreach event. Activities should be designed to take a few minutes and produce a tangible result. - Oil Spill Cleanup – Alex Madonik - Salt Water Rainbows – Sanda Sun - Sea shells and calcium carbonate – Jackie Erickson |  |
| Community Event Ideas | Learn about seafood offered in your community: - Where does it come from? - How is it caught? - Is it wild or farmed? - Is it fresh or frozen? - Fish menu recommendations (safety and sustainability) |  |
| K – 12 Illustrated Poem Contest | Illustrate Poem Contest: The Ocean Ecosystem |  |
| New Product Ideas | Staff can generally add a few new CCEW products to its line each year. Not all suggestions can be pursued, but please list any that you deem as good possibilities for staff to consider. |  |
| Online and Print Resources | List any web resources that should be passed on to staff for inclusion of the CCEW webpages. - Journal of Chemical Education - ChemMatters - Videos - PowerPoint (for teachers_ |  |
| Alignment to the National Science Ed. Standards | Report on National Science Education Standards approved by the Governing Board of the National Research Council: http://www.nap.edu/readingroom/books/nses/html/ as related to the theme. Provide the general, broad standards that relate for the 4th-6th grades. |  |