## Sheet1
Attachment A: ACS Team China 3-Year Action Plan
Objective | Strategy Alignment | Lead Division | 2014 | 2015 | 2016 | Cross-Division Synergies
Increase C&EN outreach to China’s/India’s chemistry community, through visits to academic institutions, attendance of conferences and trade shows. | Expanding Sales & Marketing Initiatives | ACS Publications - C&EN | X | X | X | Collaboration among Pubs, CAS, and membership include meetings in China with various C&EN publication and distribution partners.
Develop annual, revenue-generating country-focused supplements. | Expanding Sales & Marketing Initiatives | ACS Publications - C&EN | X | X | X | Ability to source materials beyond the Publications division.
Create C&EN China prototype in 2014; launch C&EN China in 2015. | Editorial Outreach and Sourcing | ACS Publications - C&EN | X | X |  | Collaboration with ACSI team supporting CAS for introductions.
Establish a high-level physical presence of C&EN in Asia; establish an interim base in Singapore in 2015. | Editorial Outreach and Sourcing | ACS Publications - C&EN | X | X | X | Consider members and potential CAS customer base as opportunities for subscribers
Recruit Asia-based freelance writers to increase Asia-sourced stories | Editorial Outreach and Sourcing | ACS Publications - C&EN | X | X | X | Collaborate with ACSI team for introductions
Recruit Asia-based members for C&EN’s advisory board. | Editorial Outreach and Sourcing | ACS Publications - C&EN | X | X | X
Combining membership and other outreach initiatives with ACS offerings to expand the overall ACS footprint. | Membership and Other Outreach | ACS Publications - C&EN | X | X | X | Initial verbal outreach in process; develop more formalized plan for 2015 outreach
With ACS partners and others, develop C&EN-branded country- or region-specific surveys, such as salary surveys; best places to work for; best places to do Ph.D. in chemistry; develop research into supplements | Membership and Other Outreach | ACS Publications - C&EN |  | X | X
With ACS partners and others, develop C&EN-branded conferences in Asia, the first in to be tested in China in 2 | Membership and Other Outreach | ACS Publications - C&EN |  | X | X
To continue capturing the best content authored by researchers in the region and the strongest research areas in this region | Editorial Outreach and Sourcing | ACS Publications - Editorial Development | X | X | X
To continue increasing the involvement of Chinese researchers in ACS journals, as authors, reviewers, and editors/editorial board members | Editorial Outreach and Sourcing | ACS Publications - Editorial Development | X | X | X
Engage researchers in ACS journal development through increased high quality content, editorial appointments and targeted outreach activities | Editorial Outreach and Sourcing | ACS Publications - Editorial Development | X | X | X
Increase the number of appointments of associate editor and editorial advisory board members from China (contingent upon Editors-in-chief) | Editorial Outreach and Sourcing | ACS Publications - Editorial Development | X
Enter a partnership with Peking University on ACS Publications Symposia Program for next one to two years development (by the end of 2014) | Membership and Other Outreach | ACS Publications - Editorial Development | X
Launch the first issue of ACS Excellence Asia with the Marketing and Sales teams | Expanding Sales & Marketing Initiatives | ACS Publications - Editorial Development | X
ACS Publications Symposia program’s first event | Membership and Other Outreach | ACS Publications - Editorial Development |  | X
Special conferences outreach, e.g. Pacifichem 2015 | Membership and Other Outreach | ACS Publications - Editorial Development |  | X |  | Planning underway with involvement from all ACS divisions
One or two journal centered workshops/sessions/seminars, based on the special needs of the journals and resources available | Expanding Sales & Marketing Initiatives | ACS Publications - Editorial Development |  | X
Increase the number of appointments of associate editor and editorial advisory board members from China (contingent upon Editors-in-chief; on-going) | Editorial Outreach and Sourcing | ACS Publications - Editorial Development |  | X | X
In-depth editorial outreach to top institutes led by Editors-in-Chief and Manager of Editorial Development, Asia. Candidate universities are based on journals’ scope for editors | Editorial Outreach and Sourcing | ACS Publications - Editorial Development |  | X | X
Develop author and reviewer education model with a focus on in-person interactive small session, to expand the “Publish your research 101” on-line videos | Editorial Outreach and Sourcing | ACS Publications - Editorial Development |  | X | X
ACS Publications Symposia program’s second and third events | Membership and Other Outreach | ACS Publications - Editorial Development |  |  | X
Social media (e.g. Weibo, Weixin, promote ACS ChemWorx) as part of Society initiatives | Membership and Other Outreach | Shared - All ACS Divisions | X | X | X
ACS awards to Chinese chemists across all ACS Divisions, either solo or partnered with Chinese key players (e.g. Chinese Chemical Society, Chinese Academy of Sciences) | Membership and Other Outreach | Shared - All ACS Divisions | X | X | X
Establish relationship with a recruiting agency in Beijing | Expanding Sales & Marketing Initiatives | CAS | X |  |  | Completed; hiring underway.
Hire the China Manager by July of 2014 | Expanding Sales & Marketing Initiatives | CAS | X |  |  | Completed
Hire 3-4 sales representatives in Beijing and Shanghai to focus on commercial new business development by end of 2014 | Expanding Sales & Marketing Initiatives | CAS | X |  |  | Completed
Qiong Yuan will transition from the role of Country Manager for China to Manager, Business Development Asia | Expanding Sales & Marketing Initiatives | CAS | X |  |  | Completed
Hire 4 sales representatives in Beijing, Shanghai, and Guangzhou to further expand the focus on commercial new business development | Expanding Sales & Marketing Initiatives | CAS |  | X |  | Hiring continues
Hire Director of Asia | Expanding Sales & Marketing Initiatives | CAS |  | X
Hire 1 sales representative in Shanghai | Expanding Sales & Marketing Initiatives | CAS |  |  | X
Establish at least five international Student Chapters in China by 2016. | Membership and Other Outreach | Education | X | X | X
Support the overall ACS presence in China by communicating existing ACS Education programs and products to representatives in China. | Membership and Other Outreach | Education |  | X
Explore the potential of holding a bilateral summer school on a topic of mutual interest in collaboration with a Chinese institution. | Membership and Other Outreach | Education |  |  | X
Provide resourcing support for establishing operations, assuring compliance with employment requirements, determining appropriate compensation and benefit programs, talent acquisition, managing employment contracts, service provider management (e.g., local recruiters, payroll organizations), employee lifecycle maintenance, etc. | All | HR | X | X | X
Washington IT will continue to provide required information technology services to the ACS divisional areas and Publications, including, but not limited to: application development, web presence, technology security, technology hardware and software etc. | All | Wash IT | X | X | X
Washington IT expects the following IT trends to have an impact on both National and Global Presence. And we intend to monitor these closely and provide necessary development, enhancements and resources when required: | All | Wash IT | X | X | X
o Data Analysis – greater expansion of data analysis to inspect, clean, transform, and model data with the goal of discovering useful information, suggesting conclusions, and supporting decision making | All | Wash IT | X | X | X
o Open Access – continued expansion of its open access publishing options | All | Wash IT | X | X | X
o Personalized Service Model - using information about a user—along with many other behavioral, demographic, and geographic attributes—to present content that is targeted and most useful to them. By aggregating and analyzing visitor information and leveraging that knowledge in content delivery framework, by customizing the information presented to users, in order to make each user’s experience more productive and engaging. | All | Wash IT | X | X | X
o Internet Security and Intrusion protection – expand security measures and resources to monitor Internet, network and/or system activities for malicious activity. | All | Wash IT | X | X | X
o Mobile capabilities - The digital enterprise is increasingly a mobile enterprise. Business users and customers are showing a sharp interest in mobile devices and mobile applications. Converting older legacy applications to cloud computing absorbs IT leaders, but the greater long-term value, and at the same time challenge of the transition, will be extending business applications to mobile platforms. IT must work closely with all business functions to stay ahead of the emerging and rapidly changing trends and technologies. | All | Wash IT | X | X | X
o E-commerce (electronic commerce) – identify an e-commerce solution to allow transactions to be conducted electronically on the Internet. | All | Wash IT | X | X | X
o Multi-currency – identifying a financial service that allows a variety of foreign currencies, while continuing to receive settlement and reporting in their home currency. | All | Wash IT | X | X | X
In 2013 Washington IT worked with ACS attorneys and Chinese government to reestablish our networking capabilities into China – At that time we experienced an outage with our vendor Sernet (Suzhou) Technologies Corporation - they design, manufacture and service digital subscriber lines and network servers. Currently the Internet service is working well. | All | Wash IT | X | X | X
CD Networks – CD Networks enables Global Cloud Acceleration. ACS Publications has used CD Networks over the past 2 years. | All | Wash IT | X | X | X
Chinese language publications – C&EN Chinese publications, and Chinese microsite – These currently experience some translation issues. | All | Wash IT | X | X | X
SPi Global – establish the Manila Office Site | All | Wash IT | X | X | X
Joint ACS Booth presence at the Chinese Chemical Society Meeting. Brand exposure to Chinese scientists and other attendees of the CCS meeting. Host reception for members in Beijing alongside the CCS meeting. Conduct training of trainers for Chemistry Festival volunteers Beijing, Hong Kong and Shanghai. | Membership and Other Outreach | M&SA | X
Chemistry festival - student engagement. Chemistry Festival – Beijing; Chemistry Festival – Hong Kong; Chemistry Festival – Shanghai | Membership and Other Outreach | M&SA | X
Medicinal Chemistry Symposium in collaboration with the ACS Shanghai Chapter; High quality symposium for scientists in the Pharma fields | Membership and Other Outreach | M&SA | X
Webinar series; Host at least 3 Webinars in 2014 in collaboration with the Shanghai Chapter and 1 with the CCS. Provide, where applicable, additional technical content like papers, presentations, etc. to support the webinar topic | Membership and Other Outreach | M&SA | X
ACS on Campus with expanded M&SA Module. High profile ACSoC event with highlights of ACS activities in China and M&SA PPS. | Membership and Other Outreach | M&SA | X
Develop key partners for: Content, events management, marketing and promotion, sponsorship etc. | Membership and Other Outreach | M&SA |  | X | X
Major joint Regional Meeting of the China Science Chapters | Membership and Other Outreach | M&SA |  | X | X
Expansion of the China Micro-site for China jobs posts/ forums/ blogs and meetings may be hosted in China | Membership and Other Outreach | M&SA |  | X | X
Monthly Webinar series hosted in China | Membership and Other Outreach | M&SA |  | X | X
Seminars – technical and topical | Membership and Other Outreach | M&SA |  | X | X
Office of Research Grants is currently unable to define a 3-year plan toward China, continue to monitor developments in China to determine if change is possible. | Membership and Other Outreach | Ofc Res Grants |  | X | X
Develop an approach to communicating ACS activities in China (and globally) to governance beyond the Board. Such activities might include inclusion of our high-level principles and general approach in talking points, information in Councilor Bulletin, or other vehicles. | All | OSGC | X | X |  | This effort will be coordinated with the China team representing all divisions. Committee staff liaisons from multilple divisions will be involved.
Examine expanded engagement of Chinese ACS members in Chemistry Ambassadors and related outreach. | Membership and Other Outreach | OSGC | X | X |  | Aspects of the Chemistry Ambassadors program affect the M&SA and Education divisions.
Begin assessing opportunities to enhance awareness of ACS among the Chinese public. | Membership and Other Outreach | OSGC | X |  |  | This effort will be in support of the rest of the ACS China strategy.
Explore forces shaping the future of the chemistry enterprise in China and share this information with ACS staff engaged in the country. (See proposed divisional EPIP objective below) | All | OSGC |  | X |  | A cross-divisional team of advisors is being assembled. The China strategy team will be regularly consulted.
Identify and use specific outlets to disseminate information about the ACS to Chinese audiences. | Membership and Other Outreach | OSGC |  | X | X | This effort will be in support of the rest of the ACS China strategy.
Assess applicability of current ACS public policy statements for use in China, especially to address global and China-specific issues. | Membership and Other Outreach | OSGC |  | X | X
Develop capacity for providing legal support to Human Resources and Finance within China as our presence expands. | All | OSGC | X | X | X | This effort is tightly tied to specific legal needs of the other divisions.
Understand and evaluate the financial impact to the Society(net from operations, cash flows, ROI) of strategic initiatives undertaken in the global market; | All | Finance | X | X | X
Review evaluations of planned international expansion prepared by an independent consultant for accuracy and completeness, and assess application to the Society to ensure the Society considers all aspects of expanding operations in a foreign country and is in compliance with foreign laws and financial reporting requirements; | All | Finance | X | X | X
Review and advise on foreign currency issues to minimize foreign exchange risk; assist with developing methodologies for extracting funds from BRICKS countries; | All | Finance | X | X | X
Determine tax exposure and assist with the development of tax strategies in regards to the applicability of corporate income taxes, employment considerations, employer responsibilities, employee taxes and benefits, value added and other taxes; | All | Finance | X | X | X
Determine and evaluate regulatory compliance requirements to ensure the ACS is positioned to appropriately comply and report on those requirements; | All | Finance | X | X | X
Support the operating units’ development of cost-benefit analyses of possible options for expanding into the BRICKS countries to ensure the ACS selects the most advantageous option consistent with its objectives; | All | Finance | X | X | X
Assist the operating units with the development of budgets and provide tools for financial monitoring to provide a mechanism for evaluating financial success; | All | Finance | X | X | X
Assess the impact on financial systems such as invoicing, cash application, general ledger, etc.; assist the operating units with implementing required system changes consistent with the impact analysis; | All | Finance | X | X | X
Ensure the maintenance of effective internal controls over financial transactions by assisting the operating units with reviewing current controls and implementing new ones. | All | Finance | X | X | X
It is also the Division’s goal to expand its product and service offerings. To that end, over the next 24 – 36 months, the Treasurer & CFO Division plans to explore options for expanding the product offerings of the Member Insurance Program and enlarging the Society’s current fundraising efforts to include the BRICKS countries. | All | Finance | X | X | X